## Slide 1: Student leadership board
Workshop: 3.9.17~~TOPIC: Student activities Fair and homecoming carnival

## Slide 2: Meeting agenDa
1—let’s refresh our memories!
2—Shooting for the stars
3—coming back to reality
4—Action Plan: Student activities fair
5—ACTION ITEMS

## Slide 3: REFRESHING OUR MEMORIES
What do you remember about past student activities fairs?
What do you remember about past homecoming carnivals?

## Slide 4: Shooting for the stars
Work with a partner
What would the ideal student activities fair look like?
What would the ideal homecoming carnival look like?

## Slide 5: COMING Back to reality
Work individually
What is realistic?
What is doable?
What is manageable?

## Slide 6: COMING Back to reality GALLERY WALK
Work individually
Review each pair’s ideas
Draw a  next to each idea that you believe is realistic, doable & Manageable

## Slide 7: COMING Back to reality GALLERY WALK
Work individually
Review each pair’s ideas
Draw a ? next to each idea that you believe might be too challenging to implement

## Slide 8: Action planning steps
1—recap pertinent information: (Date, Location, people, budget)
2—DETErMINE LEADERSHIP ROLES
3—BRAINSTORM PRELIMINARY TASK LIST
4—REFINE TASK LIST
5—ASSIGN TARGET COMPLETION DATES & DEADLINES TO TASKS
6—ASSIGN PEOPLE TO TASKS
7—REGULAR CHECK-INS AND REFLECTIONS ON PLAN

## Slide 9: STEP 1—RECAP PERTINENT INFORMATION
Date
Location
Budget
People:
  Chairperson / chair people
  Target audience

## Slide 10: STEP 2—DETERMINE LEADERSHIP ROLES
Which adult is lead contact?
Will you have a chairperson?
To whom will the chairperson report?

## Slide 11: STEP 3—BRAINSTORM PRELIMINARY TASK LIST
JOT EVERYTHING DOWN THAT NEEDS TO BE DONE
DON’T WORRY ABOUT THE ORDER AT THIS POINT

## Slide 12: STEP 4—REFINE TASK LIST
LOOK For REDUNDANCIES
BUILD IN REMINDERS
SOLICIT FEEDBACK FROM PEOPLE WHO HAVE RUN SIMILAR EVENTS

## Slide 13: STEP 5—ASSIGN TARGET COMPLETION DATES AND DEADLINES TO TASKS
TARGET COMPLETION DATES—NICE TO HAVE DONE BY
BE GENEROUS WITH TARGET COMPLETION DATES
DEADLINES—MUST BE DONE BY

## Slide 14: STEP 6—ASSIGN PEOPLE TO TASKS
THIS IS ALSO KNOW AS DELEGATING
Will you allow people to sign up for tasks?
  Advantages
  Disadvantages
  Online sign up options
Think about how you will hold people accountable

## Slide 15: STEP 7—REGULAR CHECK-INS & REFLECTION ON PLAN
Progress monitoring
Adjusting

## Slide 16: reminder
All Leadership presentations may be found on the CB West website, Under “Activities” > “Student leadership Board”
http://www.cbsd.org/domain/477
Please share what you’ve learned with your organization!

## Slide 17: Co-facilitator
Are you interested in co-facilitating an upcoming leadership training session with Dr. Caughie?

## Slide 18: ACTION ITEMS
1—Send Dr. Caughie name ideas for Student Leadership Board (on-going)
2—Email Dr. Caughie feedback on this session (prior to april 27)
3—Email Dr. Caughie with any needs your group has (on-going)
4—Share what you learned in this session with your peers (on-going)
5—CONNECT WITH BAILEY IF YOU’RE INTERSTED IN HELPING WITH the unity project